## Summary
Group 9C - Robot Path Navigator: Project Plan
Computing Fundamentals final project. Members: Wyatt Zani, Robert, Isaiah.
Project | Robot grid navigation: user defines grid size, start A and goal B; robot avoids randomly generated obstacles while travelling from A to B on a limited battery.
Repository | https://github.com/WyattZani/Group9c_FinalProject
Iteration 2 Project Leader | TBD - must be someone who has not led before
Iteration 2 due | 2026-10-30
Iteration 2 progress
Status | Tasks (Task Table) | Timeline items
Not started | 14 | 17
Stub | 0 | 0
In progress | 1 | 0
Done | 0 | 0
% Done | 0% | 0%
How to use this workbook
- Yellow cells are inputs - update them as work progresses.
- Status columns use a dropdown: Not started / Stub / In progress / Done. Colors update automatically.
- The progress counts above are formulas and update from the 'Iteration 2 Tasks' and 'Iteration 2 Week' tabs.
- Owners on the Iteration 2 tabs are suggestions - confirm them as a team and edit the yellow cells.
- The Project Leader keeps this file current and presents it at the check-in meeting.

## Iteration 1
Iteration 1 - Project Planning and Teamwork (due Oct 13)
Review of what was submitted against the Iteration 1 requirements. Gaps should be fixed in the Iteration 2 report.
Section | Requirement | Status | What we submitted / evidence | Gap / follow-up
1. Objectives | Individual objectives for each student | Done | Wyatt, Robert and Isaiah each listed an objective. | Make them measurable (e.g. 'write and commit the Navigator class').
1. Objectives | Shared team objectives | Not started | 'Shared' heading in the PDF was left blank. | Agree on 2-3 shared, measurable objectives.
2. Technologies | Languages, tools and frameworks chosen | Done | C++, VS Code, g++/MSVC, GitHub, test.sh, GitHub Issues, group chat, GitHub Actions. | -
2. Technologies | Reason for each choice | Done | Reason column filled in for every row. | -
3. Timeline | Major tasks and milestones | Done | Set up repo, pseudocode, coding, debug, testing, final presentation. | -
3. Timeline | Deadlines for each task | Not started | No dates in the timeline. | Added on the 'Iteration 2 Week' tab.
3. Timeline | Responsibility assigned per task | In progress | Contributions listed per person, but not tied to timeline tasks. | Owner column added on the 'Iteration 2 Tasks' tab.
3. Timeline | Expected deliverable per task | Not started | Not included. | Deliverable column added on the Iteration 2 tabs.
3. Timeline | Communication, progress tracking, handling challenges | In progress | Group chat and GitHub Issues listed as tools. | Describe how often you meet and how blockers are raised.
4. Document | Project scope and expected deliverables | Done | Section 1 'What is the project?' | -
4. Document | Contribution table (this iteration + next) | In progress | Section 5 lists contributions as bullets, not a table. | See 'Contributions' tab.
4. Document | Summary of team meetings and decisions | Not started | Not included. | See 'Meetings' tab.
4. Document | PDF uploaded to GitHub repo | Not started | PDF is not in the repository. | Add to docs/ folder.
5. Teamwork | Individual reflection and peer review | Done | Wyatt's reflection and peer ratings included. | Each member submits their own.
Code | First working draft of the program | Done | Group9FinalDraft1.cpp: full simulation in one file (grid input, obstacles, BFS route check, detour logic, battery, display). | Restructure into classes and a menu in Iteration 2.

## Iteration 2 Tasks
Iteration 2 - Task Table
Every feature is a task with a menu option. Status reflects the end of this iteration. Owners are suggestions - confirm as a team.
Task ID | Task name | Menu option | Responsible | Files / functions | Expected deliverable | Status
T0 | Menu loop and program skeleton | main | Project Leader | main.cpp: main(), printMenu(); tasks.h/.cpp: all stubs | Program compiles and every menu option runs (stub prints 'not implemented yet') | Not started
T1 | Configure grid (size, obstacle count) | 1 | Isaiah | grid.h/.cpp: Grid::setSize(), Grid::clear(); tasks.cpp: taskConfigureGrid() | User can set side length 3-10 and obstacle count with input validation | Not started
T2 | Set start A and goal B | 2 | Isaiah | input.h/.cpp: readInt(), readPoint(); tasks.cpp: taskSetPoints() | A and B entered and validated (in bounds, A != B) | Not started
T3 | Generate obstacles + route check | 3 | Isaiah | grid.cpp: Grid::placeObstacles(), Grid::pathExists(), Grid::isFree() | Battleship-style obstacles placed; layout guarantees a route from A to B | Not started
T4 | Display current grid | 4 | Wyatt | display.h/.cpp: render(), cellSymbol(); tasks.cpp: taskShowGrid() | Grid printed with A, B, obstacles, path, robot and stats | Not started
T5 | Run simulation (animated) | 5 | Robert | navigator.h/.cpp: Navigator::run(), Navigator::step(); robot.h/.cpp: Robot::move() | Robot travels A to B, detours around obstacles, uses battery | Not started
T6 | Show results of last run | 6 | Robert | navigator.cpp: Navigator::printResults(), getOutcome() | Outcome (reached / battery dead / trapped), moves, distance, battery shown | Not started
T7 | Help and legend | 7 | Wyatt | display.cpp: printHeader(), printLegend() | Program description, symbols and coordinate rules shown | Not started
T8 | Reset / new map | 8 | Wyatt | tasks.cpp: taskReset(); grid.cpp: Grid::clear(); robot.cpp: Robot::reset() | All settings cleared so a new run can be configured | Not started
T9 | Save / load map (optional) | 9 | Isaiah | grid.cpp: Grid::save(), Grid::load() | Grid layout written to and read from a text file | Not started
T10 | Run history / statistics (optional) | 10 | Robert | tasks.cpp: taskHistory() | Success rate and average moves across runs this session | Not started
T11 | Exit | 0 | Project Leader | main.cpp: case 0 | Program exits cleanly | Not started
D1 | README with build and run instructions | - | Wyatt | README.md | Description, build command, run command, menu list, team | Not started
D2 | System design (classes, menu, files, diagram) | - | All | docs/Iteration02_Report.pdf | Class list, menu design, file structure, class diagram | Not started
D3 | Project Plan (this Excel file) | - | Project Leader | docs/Project_Plan.xlsx | Task table, revised timeline, contributions kept up to date | In progress
Planned classes
Class | Private data | Public methods
Point (struct) | r, c | samePoint()
Grid | side, cells[MAX_SIDE][MAX_SIDE] | setSize(), getSize(), clear(), inBounds(), isFree(), getCell(), markVisited(), placeObstacles(), pathExists()
Robot | pos, moves, distance, battery | move(dr, dc), hasBattery(), reset(start), getters
Navigator | Grid&, Robot, A, B, phase, lane, detouring, lastForward, retreating, sideDir, outcome | run(), step(), getOutcome(), printResults()
display / input (functions) | - | render(), printHeader(), printLegend(), readInt(), readPoint()

## Iteration 2 Week
Iteration 2 - Week Plan (Sat Oct 24 - Fri Oct 30, 2026)
Day-by-day schedule. Update Status and Notes daily; the Project Leader reviews this at each check-in.
Date | Task | Owner | Deliverable | Task ID | Status | Notes
2026-10-24 | Pick Project Leader (someone who has not led before) | All | Leader named on Summary tab | T0 | Not started
2026-10-24 | Agree on task table, owners and class design | All | Task table confirmed | D2 | Not started
2026-10-25 | Commit skeleton: all .h/.cpp files, class declarations, switch menu, stubs | Project Leader | Repo compiles with g++ -std=c++17 src/*.cpp; every option prints 'not implemented yet' | T0 | Not started
2026-10-25 | Create README draft with build/run instructions | Wyatt | README.md committed | D1 | Not started
2026-10-26 | Port grid size, A/B input and obstacle generation into Grid/input files | Isaiah | Options 1-3 working | T1-T3 | Not started
2026-10-26 | Port display, header and legend into display files | Wyatt | Options 4 and 7 working | T4, T7 | Not started
2026-10-27 | Port simulation loop into Navigator and Robot classes | Robert | Option 5 working | T5 | Not started
2026-10-27 | Implement reset / new map | Wyatt | Option 8 working | T8 | Not started
2026-10-28 | Results screen; start run history | Robert | Option 6 working; option 10 stub or in progress | T6, T10 | Not started
2026-10-28 | Start save/load map | Isaiah | Option 9 stub or in progress | T9 | Not started
2026-10-28 | Check-in meeting: Leader presents status report | Project Leader | Everything compiles together; blockers recorded on Meetings tab | - | Not started
2026-10-29 | Draw class diagram; write system design section | All | Diagram + design in report | D2 | Not started
2026-10-29 | Update this Excel plan (task status, contributions) | Project Leader | Project_Plan.xlsx current | D3 | Not started
2026-10-29 | Write individual reflections | All | One reflection per member in report | D2 | Not started
2026-10-30 | Fresh-clone build test; remove old Group9FinalDraft1.cpp | All | Clean build from a new clone | T0 | Not started
2026-10-30 | Export report PDF to docs/; final push | Project Leader | docs/ has PDF + Excel | D2, D3 | Not started
2026-10-30 | Each member submits GitHub link on Canvas (by 11:59pm) | All | 3 Canvas submissions | - | Not started

## Contributions
Contribution Table
What each member completed, and their responsibilities for the next iteration.
Member | Iteration | Completed this iteration | Responsibilities for next iteration
Wyatt Zani | Iteration 1 | Set up the group repo; wrote project overview, part of technologies table, own objective and contributions; individual reflection; committed first program draft (Group9FinalDraft1.cpp). | Iteration 2: T4 display, T7 help/legend, T8 reset, D1 README.
Robert | Iteration 1 | Assisted with pseudocode; programming and most of the navigation logic; helped teammates with their sections. | Iteration 2: T5 simulation (Navigator, Robot), T6 results, T10 run history.
Isaiah | Iteration 1 | Contributed ideas and organised information; worked on the program and bug fixes; helped push repo files. | Iteration 2: T1 grid config, T2 A/B input, T3 obstacles + route check, T9 save/load.
Wyatt Zani | Iteration 2 |  | Iteration 3: TBD
Robert | Iteration 2 |  | Iteration 3: TBD
Isaiah | Iteration 2 |  | Iteration 3: TBD
Iteration 1 rows come from the Iteration 1 PDF. Fill in the Iteration 2 rows by Oct 29.

## Meetings
Team Meetings and Decisions
Record every meeting, even short group-chat check-ins.
Date | Format | Attendees | Topic | Decisions | Action items
2026-10-24 | Group chat | All | Kickoff for Iteration 2 | Example: chose Project Leader; agreed task table | Example: Leader pushes skeleton by Sun
2026-10-28 | In person / call | All | Check-in: Leader status report